## Week 4 Checklist
Week 4 Checklist
Group D - Week 4 Checklist
Focus: implement selected methods, complete initial statistical models, evaluate results, and begin report drafting.
Team Member | Role / Focus | Week 4 Task | Status | Notes / Evidence
Bel Zhou | Data Engineer / Researcher | Complete a final quality review of the historical modelling dataset and document any remaining missing values or outliers. | ☐ Not started | Confirm modelling period, row count, duplicates, interval continuity and treatment decisions.
Bel Zhou | Data Engineer / Researcher | Add the NSW public holiday indicator and any agreed final calendar features. | ☐ Not started | Update the modelling dataset and document the source and transformation.
Bel Zhou | Data Engineer / Researcher | Review lag, change and ramp features for chronological accuracy and potential data leakage. | ☐ Not started | Confirm features are generated after sorting and before chronological splitting.
Bel Zhou | Data Engineer / Researcher | Prepare the final Week 4 modelling dataset (v2) for analysis. | ☐ Not started | Retain a reproducible processed dataset and a smaller sample for GitHub if required.
Bel Zhou | Data Engineer / Researcher | Update the Data Dictionary and Data Quality Summary for all Week 4 changes. | ☐ Not started | Include feature definitions, units, sources, limitations and missing-value handling.
Bel Zhou | Data Engineer / Researcher | Prepare report-ready summary tables and additional visualisations requested during modelling. | ☐ Not started | Provide clear titles, units, notes and figure captions.
Bel Zhou | Data Engineer / Researcher | Draft the Data Description, Data Processing and Feature Engineering report sections. | ☐ Not started | Use the completed Week 3 dataset and EDA documentation as evidence.
Bel Zhou | Data Engineer / Researcher | Support interpretation and peer review of the statistical modelling outputs. | ☐ Not started | Check that conclusions are consistent with the data and research questions.
Anders Appel | Data Engineer / Analyst | Complete Pearson and Spearman correlation analyses for the selected modelling variables. | ☐ Not started | Report coefficients and explain why both measures are relevant.
Anders Appel | Data Engineer / Analyst | Complete cross-correlation analysis between PV changes and demand changes. | ☐ Not started | Identify and document the strongest short-term lag relationships.
Anders Appel | Data Engineer / Analyst | Define chronological training, validation and test periods. | ☐ Not started | Record the date boundaries and explain how the split prevents leakage.
Anders Appel | Data Engineer / Analyst | Build the baseline OLS regression model for operational demand or demand change. | ☐ Not started | Specify the target, predictors, reference categories and assumptions.
Anders Appel | Data Engineer / Analyst | Assess coefficient estimates, confidence intervals and statistical significance. | ☐ Not started | Report effect sizes in interpretable units such as MW.
Anders Appel | Data Engineer / Analyst | Complete regression diagnostics and revise the specification where required. | ☐ Not started | Check residual patterns, heteroscedasticity, autocorrelation and influential observations.
Anders Appel | Data Engineer / Analyst | Assess multicollinearity and decide which weather variables to retain. | ☐ Not started | Use correlation review and VIF or another documented diagnostic.
Anders Appel | Data Engineer / Analyst | Build an initial non-linear or alternative model, such as GAM, if appropriate. | ☐ Not started | Compare its fit and interpretability with the baseline model.
Anders Appel | Data Engineer / Analyst | Calculate initial out-of-sample MAE, RMSE and R-squared where appropriate. | ☐ Not started | Use only chronological holdout data for predictive evaluation.
Anders Appel | Data Engineer / Analyst | Document model assumptions, limitations and initial findings for the report. | ☐ Not started | Provide reproducible code, tables and concise interpretation.
William Sivieng | Project Lead | Lead the Week 4 team meeting and review progress against the project schedule. | ☐ Not started | Record decisions, owners, blockers and next actions.
William Sivieng | Project Lead | Attend the course coordinator consultation and document the feedback received. | ☐ Not started | Capture any required changes to scope, methods or deliverables.
William Sivieng | Project Lead | Coordinate the incorporation of coordinator feedback into the Week 4 work plan. | ☐ Not started | Assign owners and update the task board.
William Sivieng | Project Lead | Confirm that the selected models and evaluation measures address the three research questions. | ☐ Not started | Check alignment with effect size, time and weather variation, and predictive performance.
William Sivieng | Project Lead | Create the first full report structure and allocate section owners and peer reviewers. | ☐ Not started | Include Introduction, Literature Review, Data, Methods, Results, Discussion and Conclusion.
William Sivieng | Project Lead | Review the draft Data and Methodology sections for clarity and consistency. | ☐ Not started | Check terminology, references, figure numbering and connection to the project plan.
William Sivieng | Project Lead | Review initial modelling outputs and coordinate team interpretation. | ☐ Not started | Ensure claims distinguish association, inference and prediction.
William Sivieng | Project Lead | Confirm that the GitHub repository and project task board are current. | ☐ Not started | Check folder structure, filenames, version history and evidence links.
William Sivieng | Project Lead | Coordinate the Week 4 teamwork reflection and plan Week 5 priorities. | ☐ Not started | Document workload balance and agreed model-refinement tasks.
Current Status Summary
Team Member | Total Tasks | Complete | In Progress | Blocked
Bel Zhou | 8 | 0 | 0 | 0
Anders Appel | 10 | 0 | 0 | 0
William Sivieng | 9 | 0 | 0 | 0

## Team Deliverables
Week 4 Team Deliverables
Shared outcomes expected by the end of Week 4
Deliverable | Owner / Contributors | Status | Evidence / Link
Final Week 4 modelling dataset v2 | Bel / Anders | ☐ Not started
Final feature and data-quality documentation | Bel | ☐ Not started
Pearson, Spearman and cross-correlation analyses | Anders / Bel | ☐ Not started
Chronological training, validation and test framework | Anders / William | ☐ Not started
Baseline OLS regression and diagnostics | Anders | ☐ Not started
Initial alternative or non-linear model | Anders | ☐ Not started
Initial out-of-sample MAE, RMSE and model comparison | Anders | ☐ Not started
Draft Data and Feature Engineering report sections | Bel / William | ☐ Not started
Draft Methodology and initial Results sections | Anders / William | ☐ Not started
Coordinator consultation feedback and action log | William / All | ☐ Not started
Updated GitHub repository and task board | All | ☐ Not started
Week 4 teamwork reflection and Week 5 plan | William / All | ☐ Not started