## Week 5 Checklist
Week 5 Checklist
Group D - Week 5 Checklist
Focus: refine models, communicate findings through clear tables and figures, and complete the first full report draft.
Team Member | Role / Focus | Week 5 Task | Due Date | Status | Notes / Evidence
Bel Zhou | Data Engineer / Researcher | Complete the Week 5 reporting and visualisation learning activities. | 2 Oct 2026 | ☐ Not started | Apply the guidance on report structure, tables, figures and client-focused reporting.
Bel Zhou | Data Engineer / Researcher | Finalise the modelling dataset and resolve outstanding data-quality treatments. | 2 Oct 2026 | ☐ Not started | Document treatment of missing PV and weather values and freeze the analysis version.
Bel Zhou | Data Engineer / Researcher | Prepare publication-ready data, EDA and model-result figures. | 4 Oct 2026 | ☐ Not started | Use consistent colours, units, titles, captions and accessible labels.
Bel Zhou | Data Engineer / Researcher | Prepare report-ready tables for dataset quality, descriptive statistics and feature definitions. | 4 Oct 2026 | ☐ Not started | Keep tables concise and link each table to a research question.
Bel Zhou | Data Engineer / Researcher | Complete the Data Description, Data Processing, Feature Engineering and EDA report sections. | 5 Oct 2026 | ☐ Not started | Incorporate limitations of daily Sydney Airport weather data.
Bel Zhou | Data Engineer / Researcher | Review reproducibility and organise final analysis files in GitHub. | 5 Oct 2026 | ☐ Not started | Check scripts, filenames, folders, README instructions and processed-data sample.
Anders Appel | Data Engineer / Analyst | Refine the OLS or selected statistical model using Week 4 diagnostics. | 2 Oct 2026 | ☐ Not started | Address residual behaviour, autocorrelation, heteroscedasticity and multicollinearity.
Anders Appel | Data Engineer / Analyst | Run and evaluate the machine-learning benchmark, if feasible. | 3 Oct 2026 | ☐ Not started | Compare a tree-based or other justified benchmark against the transparent baseline.
Anders Appel | Data Engineer / Analyst | Complete chronological validation and final model comparison. | 4 Oct 2026 | ☐ Not started | Report MAE, RMSE, R-squared where appropriate, and validation-period stability.
Anders Appel | Data Engineer / Analyst | Quantify and interpret PV effects by time of day, season and weather. | 4 Oct 2026 | ☐ Not started | Provide effect sizes, uncertainty and clear links to Q1 and Q2.
Anders Appel | Data Engineer / Analyst | Assess whether PV-enhanced models improve prediction beyond the baseline. | 5 Oct 2026 | ☐ Not started | Directly address Q3 using out-of-sample metrics.
Anders Appel | Data Engineer / Analyst | Write the Methods and Results sections and provide reproducible outputs. | 5 Oct 2026 | ☐ Not started | Include model specifications, assumptions, diagnostics, tables and figure references.
William Sivieng | Project Lead | Complete the Week 5 reporting learning activities and confirm the intended report audience. | 2 Oct 2026 | ☐ Not started | Apply client-focused structure and non-technical communication principles.
William Sivieng | Project Lead | Combine all report sections into the first complete group report draft. | 5 Oct 2026 | ☐ Not started | Ensure the draft includes all required sections and references.
William Sivieng | Project Lead | Review workload allocation and reassign tasks where needed. | 2 Oct 2026 | ☐ Not started | Keep report, modelling and presentation work balanced across the team.
William Sivieng | Project Lead | Edit the Introduction, Literature Review and project framing. | 4 Oct 2026 | ☐ Not started | Ensure the research gap, objectives and success criteria remain clear.
William Sivieng | Project Lead | Coordinate peer review of all tables, figures and analytical claims. | 5 Oct 2026 | ☐ Not started | Confirm every major output is reviewed by another member.
William Sivieng | Project Lead | Create the Week 6 report finalisation and presentation production plan. | 5 Oct 2026 | ☐ Not started | Assign slide, script, recording, editing and quality-assurance owners.
Current Status Summary
Team Member | Total Tasks | Complete | In Progress | Blocked | Completion %
Bel Zhou | 6 | 0 | 0 | 0 | 0%
Anders Appel | 6 | 0 | 0 | 0 | 0%
William Sivieng | 6 | 0 | 0 | 0 | 0%

## Week 6 Checklist
Week 6 Checklist
Group D - Week 6 Checklist
Focus: finalise the report by 8 October 2026 and complete the video presentation by 9 October 2026.
Team Member | Role / Focus | Week 6 Task | Due Date | Status | Notes / Evidence
Bel Zhou | Data Engineer / Researcher | Complete the Week 6 presenting learning activities. | 6 Oct 2026 | ☐ Not started | Focus on presenting to non-technical audiences, key messages and audience engagement.
Bel Zhou | Data Engineer / Researcher | Finalise all report figures, tables, captions and appendices. | 7 Oct 2026 | ☐ Not started | Check consistency, readability, numbering and cross-references.
Bel Zhou | Data Engineer / Researcher | Complete final data and code reproducibility checks. | 7 Oct 2026 | ☐ Not started | Confirm the analysis can be rerun from documented inputs and scripts.
Bel Zhou | Data Engineer / Researcher | Proofread the Data, EDA and Feature Engineering sections. | 7 Oct 2026 | ☐ Not started | Correct terminology, units, limitations and factual consistency.
Bel Zhou | Data Engineer / Researcher | Prepare presentation visuals and concise explanations for data and EDA findings. | 8 Oct 2026 | ☐ Not started | Translate technical results into clear messages for a non-technical audience.
Bel Zhou | Data Engineer / Researcher | Complete final GitHub organisation and archive submission-ready outputs. | 9 Oct 2026 | ☐ Not started | Ensure final report, code, figures and supporting documentation are clearly located.
Anders Appel | Data Engineer / Analyst | Freeze final model specifications and regenerate all model outputs. | 6 Oct 2026 | ☐ Not started | Ensure report tables and figures match the final code and dataset.
Anders Appel | Data Engineer / Analyst | Complete final diagnostics, sensitivity checks and limitations. | 6 Oct 2026 | ☐ Not started | Document uncertainty and any findings that are not robust.
Anders Appel | Data Engineer / Analyst | Proofread the Methods and Results sections. | 7 Oct 2026 | ☐ Not started | Ensure model claims accurately distinguish explanation, inference and prediction.
Anders Appel | Data Engineer / Analyst | Prepare presentation slides and script for modelling and results. | 8 Oct 2026 | ☐ Not started | Explain key effect sizes and model performance without unnecessary technical detail.
Anders Appel | Data Engineer / Analyst | Complete a final numerical consistency check across report, slides and script. | 9 Oct 2026 | ☐ Not started | Confirm coefficients, metrics, dates and sample sizes agree everywhere.
Anders Appel | Data Engineer / Analyst | Participate in the full presentation rehearsal and final recording. | 9 Oct 2026 | ☐ Not started | Address timing, handovers, audio and clarity issues.
William Sivieng | Project Lead | Confirm the presentation key message and narrative for a non-technical audience. | 6 Oct 2026 | ☐ Not started | Keep the story centred on the research questions and practical significance.
William Sivieng | Project Lead | Coordinate final report editing, references, formatting and contribution statements. | 7 Oct 2026 | ☐ Not started | Ensure one consistent voice and compliance with assessment requirements.
William Sivieng | Project Lead | Complete final peer review and approve the report for completion. | 8 Oct 2026 | ☐ Not started | Target: report fully completed by 8 October 2026.
William Sivieng | Project Lead | Build and integrate the complete presentation deck. | 8 Oct 2026 | ☐ Not started | Use a clear opening, methods overview, key findings, limitations and conclusion.
William Sivieng | Project Lead | Coordinate scripts, speaking allocations and handovers. | 8 Oct 2026 | ☐ Not started | Balance speaking time and make responsibilities explicit.
William Sivieng | Project Lead | Lead a timed rehearsal and coordinate final video recording and editing. | 9 Oct 2026 | ☐ Not started | Target: video presentation fully completed by 9 October 2026.
William Sivieng | Project Lead | Run final submission-readiness checks for report and video files. | 9 Oct 2026 | ☐ Not started | Check filenames, formats, playback, permissions and backup copies.
Current Status Summary
Team Member | Total Tasks | Complete | In Progress | Blocked | Completion %
Bel Zhou | 6 | 0 | 0 | 0 | 0%
Anders Appel | 6 | 0 | 0 | 0 | 0%
William Sivieng | 7 | 0 | 0 | 0 | 0%

## Milestones
Weeks 5–6 Milestones
Internal completion targets for the Group Report and Video Presentation
Milestone | Target Date | Owner | Status | Completion Evidence
First complete report draft | 5 Oct 2026 | William / All | ☐ Not started | All sections combined and available for peer review
Final analysis outputs frozen | 6 Oct 2026 | Anders / Bel | ☐ Not started | Final dataset, code, metrics, figures and model tables
Final report peer review complete | 7 Oct 2026 | All | ☐ Not started | Comments resolved and numerical consistency confirmed
Group report completed | 8 Oct 2026 | William / All | ☐ Not started | Final report approved and saved in submission-ready format
Presentation deck and scripts completed | 8 Oct 2026 | All | ☐ Not started | Final slides, scripts and speaking allocations
Video presentation completed | 9 Oct 2026 | William / All | ☐ Not started | Final video reviewed for content, timing, audio and playback
Video upload practice / submission check | 9 Oct 2026 | William / All | ☐ Not started | Upload process checked and backup retained