GROUP PROJECT PLAN

# Rooftop Solar Variability and Short-Term Grid Demand

A data science study of how distributed rooftop solar photovoltaic (PV) output reshapes operational demand in Australia’s National Electricity Market (NEM)

RESEARCH QUESTION Quantify the impact of rooftop solar generation variability on grid demand across different times of the day and under varying weather conditions.

| Field | Details |
| --- | --- |
| Course | ZZSC9020 |
| Team | Group D |
| Members | Bel Zhou (z5537223); Anders Appel (z5568978); [William Sivieng] (z3023671) |

Table of Contents

1. Introduction and Motivation	2

2. Brief Preliminary Literature Review	2

3. Methods, Software and Data Description	3

4. Activities, Roles and Schedule	4

References	5

PAGE 1 OF 3

# 1. Introduction and Motivation

From 2020 to 2025, rooftop solar doubled in contribution to electricity generated in Australia and currently accounts for approximately 14% (Clean Energy Council, 2026). Since rooftop solar generation happens behind the meter, more solar power at home means less electricity is required from the grid. This can make the midday dip in demand even deeper and cause much sharper spikes in the afternoon when solar production starts to drop off. Understanding these rapid shifts is essential for predicting demand, coordinating battery storage, and keeping the whole electricity system running reliably. This directly serves system operators and retailers, who must anticipate rapid demand swings in real time to avoid costly imbalance exposure.

This project aims to measure how half-hourly changes in estimated rooftop solar output relate to New South Wales (NSW) grid demand. We will look at how this connection changes depending on the time of day and the weather, all while accounting for regular patterns like the day of the week or the season.

PROJECT OBJECTIVE Create a reproducible Python workflow to profile, model, and visualize the short-term link between solar variability and grid demand, considering weather factors and time lags.

## Research questions and success criteria

| Research question | Planned output | Success evidence |
| --- | --- | --- |
| Q1. How strongly are half-hourly PV changes linked to demand changes? | Correlation, regression and effect size in MW. | Coefficient uncertainty and diagnostics. |
| Q2. How does this effect change based on time and weather? | Results broken down by hour, season, and weather. | Stable patterns across validation periods. |
| Q3. Does PV improve short-term demand prediction beyond the available forecast? | Comparison of forecast, internal non-PV baseline, and PV-enhanced models. | Out-of-sample MAE and RMSE. |

# 2. Brief Preliminary Literature Review

Yan and Han (2023) investigated how rooftop solar impacts wholesale electricity demand within Australia's NEM by applying state-level regression models to half-hourly data. They discovered that rooftop PV lowers daytime grid demand, helping create a duck-curve demand profile providing a way to quantify the relationship between rooftop PV and demand patterns.

Houchati, Beitelmal, and Khraisheh (2022) employed support vector regression, combining PV, energy consumption, and weather data to forecast rooftop solar output achieving over 90% accuracy on sunny days. This underscores the importance weather variables are when you're trying to model solar variability.

Yildiz et al. (2018) evaluated short-term forecasting models for behind-the-metre rooftop PV solar generation and residential electricity demand in NSW across multiple temporal resolutions. They were able to show that weather-augmented models substantially reduced forecasting error during periods of rapid solar output swings which directly validates our proposed approach.

Bae, Kwon, and Song (2021) explored how behind-the-metre PV distorts grid demand, proposing an Extreme Gradient Boosting (XGBoost) forecasting model to help address this. By estimating the actual PV generation and reconstructing true electric load, they significantly reduced prediction errors when compared with previous baseline models. This demonstrates a method of how to handle unmetered rooftop PV data and the use of XGBoost for short-term demand prediction.

Sinclair, Shepley, and Hajati (2026) test whether transformer architectures can outperform AEMO's own operational forecast for intraday NEM spot prices. Though focused on price rather than demand, they show AEMO's forecast is consistently beatable by modern deep learning, with predictive power driven mainly by AEMO's own forward-looking forecasts rather than historical patterns.

Together, these studies confirm rooftop PV measurably reshapes NEM demand, that weather features are essential to modelling this reshaping, and that AEMO's forecast is a genuinely beatable benchmark. No reviewed study jointly quantifies half-hourly PV-driven demand variability while benchmarking against AEMO's operational forecast, the gap this project addresses.

PAGE 2 OF 3

# 3. Methods, Software and Data Description

## Methods and software

First, we will use exploration analysis and visualisation to compare how solar generation and demand patterns change based on the time of day and weather conditions. We will also run correlation and cross-correlation analyses to spot specific relationships and any potential lag effects. To estimate the impact of rooftop PV, we will use OLS or generalised additive regression, making sure to control for variables like the hour, weekday, season, and weather. We also plan to set up a machine-learning benchmark, using something like gradient-boosted trees, to see if non-linear interactions help improve our predictions. To keep things honest and prevent future information from leaking into earlier periods, we will use chronological splits for training, validation, and testing.

Python will be our primary language for this project. For data preparation, we will likely use pandas or polars along with NumPy. We will use Matplotlib or Seaborn for our charts, and statsmodels or pyGAM for statistical modelling. For the machine-learning benchmarks, we will rely on scikit-learn combined with XGBoost or LightGBM. We will also use Git to manage version control and help the team collaborate. The full analysis will be developed and documented in a Jupyter Notebook, ensuring the workflow is reproducible and that code, outputs, and interpretation sit together in one report. Findings will then be summarized in a PowerPoint for a video presentation.

Teams will be the main communication method for regular updates with a video call booked in for once a week. Microsoft Planner will be used as a task board to track individual tasks.

## Data description

| Dataset | Variables and format | Relevance and issues |
| --- | --- | --- |
| AEMO rooftop PV actual | CSV or table containing timestamps, regions, PV generation in MW, and quality indicators. | This is our main explanatory variable. General data quality checks to address estimate revisions, duplicates, and data gaps (if any). |
| AEMO operational demand | CSV or table containing timestamps, regions, and demand in MW. | This is our outcome variable. General data quality checks. |
| BoM Gridded Daily Solar Exposure | CSV or API extracts. | Solar irradiance measured by the absorption of atmospheric water vapour and cloud albedo reflection from space. Limited by daily interval. |
| BoM Half-Hourly Station Data | CSV or API extracts. | Half-hourly localised weather data including temperature, humidity, and critical visual estimates of cloud cover. |
| Solcast Data | API extract. | Alternate source of irradiance and weather data. |
| Calendar data | Derived fields like hour, weekday, month, season, and holidays. | These help control recurring demand patterns. We also need to double-check time zones and daylight-saving changes. |

The data provided for this project is enhanced with additional sources: half-hourly rooftop PV generation from AEMO (via NEMOSIS), continuous solar exposure and cloud cover observations from the Bureau of Meteorology, higher-resolution cloud opacity from the Solcast API for specific high-impact periods, and calendar data. The final combined data set will consist of half-hourly observations across NSW. Depending on our scope, several years of data could result in hundreds of thousands of rows. The main challenge will be merging different sources that have different timestamps, locations, and revision cycles.

## Processing and evaluation

To get started, we will standardise all timestamps and region codes, then fix any issues with daylight-saving duplicates or missing intervals. After that, we will join the PV, demand, weather, and calendar data while keeping a log of data quality. We will also create new features like changes and ramps, such as delta PV and delta Demand, along with 30 to 120-minute lag features. Finally, we will evaluate our statistical models using effect sizes, confidence intervals, and residual checks, while using MAE and RMSE to measure our prediction accuracy.

PAGE 3 OF 3

# 4. Activities, Roles and Schedule

To keep things organised, our team will use a shared repository, a task board, and hold weekly check-ins. We will make sure to document all major decisions regarding scope, data, and modelling. Also, to ensure accuracy, every analytical output will be peer-reviewed by another team member before it goes into the final report.

While each team member holds a primary role, responsibilities will be shared collaboratively throughout the project, with roles adjusted as needed in an agile manner to respond to emerging challenges and workload.

## Primary role allocation and justification

| Member | Primary role | Responsibilities | Justification |
| --- | --- | --- | --- |
| Bel Zhou | Data Engineer / Researcher | Acquiring, joining, and validating data; maintaining the data dictionary; supporting literature reviews and interpretation. | Bachelor of Computer Science and Business Analysis and current Master of Data Science studies, combined with professional experience using SQL and Python to transform raw data into actionable insights. |
| Anders Appel | Data Engineer / Analyst | Acquiring, joining and validating data; building robust and structured data pipelines; data modelling and analysis; supporting report drafting and interpretation of results. | Bachelor in Electrical Engineering and professional experience as a Data Scientist and Software Developer. With a deep understanding of the NEM through previous directly relevant projects, he possesses critical insights into complexities of demand forecasting. |
| William Sivieng | Project Lead | Coordinating project scope, timelines, and deliverables; overseeing integration of team inputs into a cohesive final report. | 20+ years managing and leading insurance pricing and actuarial projects, and presenting technical findings to Executive stakeholders. |

## Main activities and schedule

| Activity | W1-2 | W3 | W4 | W5 | W6 |
| --- | --- | --- | --- | --- | --- |
| Topic, plan and roles | ● |  |  |  |  |
| Literature review | ● | ● |  |  |  |
| Data collection and cleaning | ● | ● | ● |  |  |
| EDA and feature engineering |  | ● | ● |  |  |
| Modelling and analysis |  |  | ● | ● |  |
| Visualisation and interpretation |  |  |  | ● | ● |
| Report writing |  |  | ● | ● | ● |
| Final review and submission |  |  |  |  | ● |

## Weekly deliverables

•  Week 1-2: Finalise the topic, set up Github, project plan, roles, literature sources, and target datasets. Begin data collection and cleaning.

•  Week 3: Continue data collection and cleaning. Begin EDA and feature engineering.

•  Week 4: Work on feature engineering, run correlation and regression analyses, and initial models. Start drafting the report.

•  Week 5: Refine the models, try to test an ML benchmark, if possible, create visuals, and interpret the results.

•  Week 6: Wrap up the analysis, pull the report together, review and proofread everything, and submit the project report. PowerPoint presentation completed for use in video presentation submission.

REFERENCES | EXCLUDED FROM PAGE COUNT

# References

Australian Energy Market Operator (AEMO) 2026a, Australian Solar Energy Forecasting System, AEMO, viewed 5 September 2026.

Australian Energy Market Operator (AEMO) 2026b, MMS Data Model Report: ROOFTOP_PV_ACTUAL, AEMO, viewed 5 September 2026.

Australian Energy Market Operator (AEMO) 2026c, Operational demand data, AEMO, viewed 5 September 2026.

Bae, D-J, Kwon, B-S & Song, K-B 2021, 'XGBoost-Based Day-Ahead Load Forecasting Algorithm Considering Behind-the-Meter Solar PV Generation', Energies, vol. 15, no. 1, article 128.

Bureau of Meteorology (BOM) 2026a, About weather station data, Australian Government, viewed 6 September 2026, <https://www.bom.gov.au/climate/data/stations/about-weather-station-data.shtml>.

Bureau of Meteorology (BOM) 2026b, Gridded daily solar exposure metadata, Australian Government, viewed 6 September 2026, <https://www.bom.gov.au/climate/austmaps/metadata-daily-solar-exposure.shtml>.

Clean Energy Council 2026, Rooftop solar and storage report: July–December 2025, Clean Energy Council, viewed 6 September 2026, <https://cleanenergycouncil.org.au/news-resources/rooftop-solar-and-storage-report-july-to-dec-2025>.

Houchati, M, Beitelmal, AH & Khraisheh, M 2022, “Predictive Modelling for Rooftop Solar Energy Throughput: A Machine Learning-Based Optimization for Building Energy Demand Scheduling”, Journal of Energy Resources Technology, vol. 144, no. 1, article 011302.

Sinclair, M, Shepley, AJ & Hajati, F 2026, Learning the grid: transformer architectures for electricity price forecasting in the Australian National Market, Applied Sciences, vol. 16, no. 1, article 75.

Solcast 2026, Solcast API documentation, DNV, viewed 6 September 2026, <https://docs.solcast.com.au>.

Yan, G & Han, L 2023, “The impact of rooftop solar on wholesale electricity demand in the Australian National Electricity Market”, Frontiers in Energy Research, vol. 11, article 1197504.

Yildiz, B, Bilbao, JI, Dore, J & Sproul, AB 2018, 'Short-term forecasting of individual household electricity loads with investigating impact of data resolution and forecast horizon', Renewable Energy and Environmental Sustainability, vol. 3, article 3.