## Week 3 Checklist
Week 3 Checklist
Group D - Week 3 Checklist
Update the status dropdown and add notes or evidence as each task is completed.
Team Member | Role / Focus | Week 3 Task | Status | Notes / Evidence
Bel Zhou | Data Engineer / Researcher | Finalise and validate the NSW1 rooftop PV and operational demand datasets. | ☐ Not started | Record dataset coverage, row counts and validation outcomes.
Bel Zhou | Data Engineer / Researcher | Standardise timestamps and resolve missing intervals, duplicates and daylight-saving issues. | ☐ Not started | Document each issue and resolution in the data quality log.
Bel Zhou | Data Engineer / Researcher | Complete the merged NSW1 modelling dataset. | ☐ Not started | Join PV, demand, weather and calendar data where available.
Bel Zhou | Data Engineer / Researcher | Create calendar features: hour, weekday, month, season and public holiday indicator. | ☐ Not started | Add definitions and data types to the Data Dictionary.
Bel Zhou | Data Engineer / Researcher | Create change and ramp variables for PV and operational demand. | ☐ Not started | Include ΔPV and ΔDemand.
Bel Zhou | Data Engineer / Researcher | Create initial lag features for 30, 60 and 120 minutes. | ☐ Not started | Check that feature creation does not introduce future-data leakage.
Bel Zhou | Data Engineer / Researcher | Update the Data Dictionary and data quality documentation. | ☐ Not started | Include source, unit, transformation and known limitations.
Bel Zhou | Data Engineer / Researcher | Add 1–2 relevant sources on time-series feature engineering or PV variability. | ☐ Not started | Summarise relevance to the project methodology.
Anders Appel | Data Engineer / Analyst | Complete the Week 3 learning content on statistical tools, machine learning and dimensionality reduction. | ☐ Not started | Summarise key implications for the project.
Anders Appel | Data Engineer / Analyst | Perform initial EDA on the merged modelling dataset. | ☐ Not started | Produce summary statistics for demand, PV and available weather variables.
Anders Appel | Data Engineer / Analyst | Analyse intraday, weekday and seasonal patterns in demand and rooftop PV. | ☐ Not started | Save clear charts and concise observations.
Anders Appel | Data Engineer / Analyst | Explore the relationship between PV changes and demand changes. | ☐ Not started | Include correlation and preliminary cross-correlation results.
Anders Appel | Data Engineer / Analyst | Assess the suitability of OLS, GAM and a tree-based machine-learning benchmark. | ☐ Not started | Document strengths, limitations and selection criteria.
Anders Appel | Data Engineer / Analyst | Assess multicollinearity among candidate explanatory variables. | ☐ Not started | Review whether PCA or other dimensionality reduction is warranted.
Anders Appel | Data Engineer / Analyst | Propose the chronological train, validation and test design. | ☐ Not started | Ensure the split prevents future-information leakage.
Anders Appel | Data Engineer / Analyst | Create and document the preliminary modelling workflow for Week 4. | ☐ Not started | Specify inputs, target, baseline and evaluation metrics.
William Sivieng | Project Lead | Review Week 2 deliverables and identify any outstanding actions. | ☐ Not started | Update the team task board and owners.
William Sivieng | Project Lead | Coordinate the Week 3 team check-in and teamwork reflection. | ☐ Not started | Record decisions, blockers and agreed next steps.
William Sivieng | Project Lead | Confirm that Week 3 activities remain aligned with the research questions and project scope. | ☐ Not started | Document any approved scope changes.
William Sivieng | Project Lead | Draft the report structure for data, EDA, methodology, results and discussion. | ☐ Not started | Assign section owners and peer reviewers.
William Sivieng | Project Lead | Define the evaluation framework with the team. | ☐ Not started | Document MAE, RMSE, coefficient uncertainty and diagnostic requirements.
William Sivieng | Project Lead | Review Bel's data documentation and Anders' EDA or modelling plan. | ☐ Not started | Record feedback and required follow-up actions.
William Sivieng | Project Lead | Check that literature review and references are consistent and correctly formatted. | ☐ Not started | Track missing citations or formatting issues.
William Sivieng | Project Lead | Confirm the GitHub repository is current and Week 3 files are stored in relevant folders. | ☐ Not started | Check filenames, folder structure and version history.
Current Status Summary
Team Member | Total Tasks | Complete | In Progress | Blocked
Bel Zhou | 8 | 0 | 0 | 0
Anders Appel | 8 | 0 | 0 | 0
William Sivieng | 8 | 0 | 0 | 0

## Team Deliverables
Week 3 Team Deliverables
Shared outcomes expected by the end of Week 3
Deliverable | Owner / Contributors | Status | Evidence / Link
Cleaned and merged NSW1 modelling dataset | Bel / Anders | ☐ Not started
Updated Data Dictionary and data quality log | Bel | ☐ Not started
Initial EDA notebook and charts | Anders / Bel | ☐ Not started
Engineered calendar, change, ramp and lag features | Bel / Anders | ☐ Not started
Statistical and machine-learning model selection rationale | Anders | ☐ Not started
Chronological validation and evaluation plan | Anders / William | ☐ Not started
Updated literature review and references | Bel / William | ☐ Not started
Updated GitHub repository and task board | William / All | ☐ Not started
Week 3 teamwork reflection and check-in record | William / All | ☐ Not started